## Marcus Queiro(Sound Effects)
Assets | Task | Who | Priority | Status | Due Date
Sound
Playable Character
Footsteps
Weapon Sounds(Gun, Blade)
Death
Abilities(Dash, Double Jump, Magnetic Hook, Electric Run, Invisible Dash)
Hurt
Pick up items
Enemies
Hunter pounce
Hunter hurt
Hunter death
Walker rifle
Walker melee
Walker death
Walker hurt
Environment
Level Background
Player Interaction
Coding
Art
Unity/Level Design

## Joseph Pak (Poducer and Design)
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Not Started | 2023-09-11
GDD | Rework The GDD | Joseph | High | In Progress | 2023-09-09

## Wyatt(Artist)
Assets | Task | Who | Priority | Status | Due Date
Game Art
| Running Animation |  | Medium | Not Started | 2023-09-30
| Platform Art |  | High | Not Started | 2023-09-23
| Tutorial Drawings |  | Low | Not Started | 2023-10-02
Coding
| Menu Escape |  | High | Not Started | 2023-09-12
| Volume |  | High | Not Started | 2023-09-12

## Emanuel(designer)
Assets | Task | Who | Priority | Status | Due Date
UI & Menu
Player UI | Health Bar | Emanuel | High | N/a | N/a
Player UI | Enegry Bar | Emanuel | High | N/a | N/a
Pause/Main Menu | Menu icons | Emanuel | Med | N/a | N/a
Pause/Main Menu | Menu Border | Emanuel | Med | N/a | N/a
Pause/Main Menu | Redesign Background | Emanuel | Med | N/a | N/a

## Raphael Brown(Programmer)
Assets | Task | Who | Priority | Status | Due Date