## Marcus Queiro(Sound Effects)
Assets | Status | Date
Sound
Playable Character
Footsteps | N/A | N/A
Weapon Sounds(Gun, Blade) | Done | Sept 8th
Death | Done | Sept 8th
Abilities(Dash, Double Jump, Magnetic Grab, Claw Grip, Water Pump) | Done | Sept 26th
Hurt | Done | Sept 8th
Pick up items | Done | Sept 8th
Enemies
Hunter pounce | Done | Sept 12th
Hunter hurt | Done | Sept 12th
Hunter death | Done | Sept 12th
Walker rifle | Done | Sept 18th
Walker death | Done | Sept 18th
Walker hurt | Done | Sept 18th
Environment
Player Interaction | Done | Sept 24th
Level 1 Music | Done | Sept 24th
Level 2 Music | Done | Sept 24th
Level 3 Music | Done | Sept 24th
Level 4 Music | Done | Sept 24th
UI
Button Sound | Done | Sep 8th
Beta Results
Dark Synthwave Music |  | Nov 15th
Respawn noise |  | Nov 15th
Fix switch noise(too loud) |  | Nov 15th
Adjustment of footsetps being too loud |  | Nov 15th

## Joseph Pak (Poducer and Design)
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms still | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Completed | 2023-09-11
GDD | Rework The GDD | Joseph | High | Completed | 2023-09-13
Level | Area 1 minimap | Joseph | High | Completed | 2023-09-15
Level | Area 2 minimap | Joseph | High | Completed | 2023-09-19
Level | Area 3 minimap | Joseph | High | Completed | 2023-09-19
Level | Area 4 minimap | Joseph | High | Completed | 2023-09-19
Level | World Map | Joseph | High | Completed | 2023-09-14
Level | Platform moving | Joseph | med | Not Started | 2023-09-23
Level | Area 1 skeleton | Joseph | High | Completed | 2023-09-19
Level | Area 2 skeleton | Joseph | High | In Progress | 2023-09-19
Level | Area 3 skeleton | Joseph | High | In Progress | 2023-09-26
Level | Area 4 skeleton | Joseph | High | In Progress | 2023-09-26
Level | One-way Platforms | Joseph | Med | Completed | 2023-09-11
Level | Area 1 | Joseph | High | Completed | 2023-10-01
Level | Area 2 | Joseph | High | Completed | 2023-10-01
Level | Area 3 | Joseph | High | In Progress | 2023-10-01
Level | Area 4 | Joseph | High | In Progress | 2023-10-01

## Wyatt(Artist)
Assets | Task | Who | Priority | Status | Due Date
Game Art
| Running Animation |  | Medium | Not Started | 2023-09-30
| Platform Art |  | High | Not Started | 2023-09-23
| Tutorial Drawings |  | Low | Not Started | 2023-10-02
| Enemy Art |  | High | Not Started | 2023-09-25
| Outermost Background |  | Medium | Not Started | 2023-10-02
Coding
| Menu Escape |  | High | Finished | 2023-09-12
| Volume |  | High | Finished | 2023-09-12
| Fullscreen toggle |  | Medium | Not Started | 2023-10-02

## Emanuel(designer)
Assets | Task | Who | Priority | Status
UI & Menu
Player UI/ Looks | Health Bar | Emanuel | High | Finished
Player UI/ Looks | Enegry Bar | Emanuel | High | Finished
Pause/Main Menu | Menu icons | Emanuel | Med | Finished
Pause/Main Menu | Menu Border | Emanuel | Med | Finished
Pause/Main Menu | Menu Buttons Fix | Emanuel | High | Finished
Pause/Main Menu | Create a Control Panel | Emanuel | Med | Finished
VFX
Particle Effect | Fire | Emanuel | Low | N/a
Shader/ Particle Effect | Lava Pool/ Shader | Emanuel | Low | N/a
Game Assets
Health pack | Find & import a placeholder | Emanuel | Low | Finished
Traps | Find & import a placeholder | Emanuel | Low | Finished
Key Card | Find & import a placeholder | Emanuel | Low | Finished
Asset Packs
Forest Pack | Find & Import pack | Emanuel | Low | Finished
Sci-fi Pack | Find & Import pack | Emanuel | Low | Finished

## Raphael Brown(Programmer)
Assets | Task | Who | Priority | Status | Due Date
Coding | Door with a lock and a key (check for fix) | Raphael Brown | High | Completed | 2023-04-17
Coding | Lava – on the floor and on walls (are like spikes) | Raphael Brown | High | Not Started
Coding | Magnetic hooks (use magnetic grab to latch on) | Raphael Brown | High
Coding | Magnetic box (use magnetic grab to pick up) | Raphael Brown | High
Coding | Vines | Raphael Brown | High
Coding | Spikes (damage players and push them back) | Raphael Brown | High
Coding | Crushers (fall on players and hurt them a lot) | Raphael Brown | High
Coding | Saw (likes spikes but moves) | Raphael Brown | Med
Coding | Crates (breakable tiles but respawn when player leave room) | Raphael Brown | Med
2023-03-10
coding | Dash | Raphael Brown | High | Completed | 2023-09-19
coding | Water Pump shoot | Raphael Brown | High | Not Started | 2023-09-19
coding | Water pump jump | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab box | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab shoot | Raphael Brown | High | Not Started | 2023-09-26
coding | Claw wall climb. | Raphael Brown | High | Not Started
2023-03-10
coding | Walk | Raphael Brown | High | Completed | 2023-03-10
coding | Jump | Raphael Brown | High | Completed
coding | Fix sticking to walls (ground check need to be changed.) | Raphael Brown | High | Not Started | 2023-09-19
coding | Water pump button | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab button | Raphael Brown | High | Not Started | 2023-09-19
coding | Energy resource (use for combat) | Raphael Brown | High | Not Started | 2023-09-19
coding | Water resource (used for pump) | Raphael Brown | High | Not Started
coding | Saving System | Raphael Brown
coding | Save rooms that track progress and what the player has | Raphael Brown
coding | Check point system(For falling into pits and lava) | Raphael Brown
Enemy AI | Walk | Raphael Brown
Enemy AI | Shoot player. | Raphael Brown
Enemy AI | Attack player – melee | Raphael Brown
Enemy AI | Spawner (when player leaves room) | Raphael Brown
Enemy AI | HP | Raphael Brown