## Marcus Queiro(Sound Effects)
Assets | Status
Sound
Playable Character
Footsteps | N/A
Weapon Sounds(Gun, Blade) | Draft Done
Death | Draft Done
Abilities(Dash, Double Jump, Magnetic Hook, Electric Run, Invisible Dash)
Hurt | Draft Done
Pick up items | Done
Enemies
Hunter pounce | Draft Done
Hunter hurt | Draft Done
Hunter death | Draft Done
Walker rifle | Draft Done
Walker death | Done
Walker hurt | Draft Updated
Enemy hit | Draft Done
Environment
Level Background
Player Interaction
UI
Button Sound | Done

## Joseph Pak (Poducer and Design)
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms still | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Completed | 2023-09-11
GDD | Rework The GDD | Joseph | High | Completed | 2023-09-13
2023-09-15
Level | Mini Map layout | Joseph
Level | Area 1 minimap | Joseph
Level | Area 2 minimap | Joseph
Level | Area 3 minimap | Joseph
Level | Area 4 minimap | Joseph
Level | Area 5 minimap | Joseph
Level | World Map | Joseph
Level | Platform moving | Joseph
Level | Area 1 | Joseph
Level | Area 2 | Joseph
Level | Area 3 | Joseph
Level | Area 4 | Joseph
Level | Area 5 | Joseph

## Wyatt(Artist)
Assets | Task | Who | Priority | Status | Due Date
Game Art
| Running Animation |  | Medium | Not Started | 2023-09-30
| Platform Art |  | High | Not Started | 2023-09-23
| Tutorial Drawings |  | Low | Not Started | 2023-10-02
| Enemy Art |  | High | Not Started | 2023-09-25
| Outermost Background |  | Medium | Not Started | 2023-10-02
Coding
| Menu Escape |  | High | Not Started | 2023-09-12
| Volume |  | High | Not Started | 2023-09-12
| Fullscreen toggle |  | Medium | Not Started | 2023-10-02

## Emanuel(designer)
Assets | Task | Who | Priority | Status | Due Date
UI & Menu
Player UI | Health Bar | Emanuel | High | N/a | N/a
Player UI | Enegry Bar | Emanuel | High | N/a | N/a
Pause/Main Menu | Menu icons | Emanuel | Med | N/a | N/a
Pause/Main Menu | Menu Border | Emanuel | Med | N/a | N/a
Pause/Main Menu | Redesign Background | Emanuel | Med | N/a | N/a
VFX
Particle Effect | Fire | Emanuel | Low | N/a | N/a
Shader/ Particle Effect | Lava Pool/ Shader | Emanuel | Low | N/a | N/a
Level
Room | Design a Save Room | Emanuel | High | N/a | N/a
Room | Design a Resource Room | Emanuel | High | N/a | N/a

## Raphael Brown(Programmer)
Assets | Task | Who | Priority | Status | Due Date
Door with a lock and a key
Lava – on the floor and on walls (are like spikes)
Magnetic hooks (use magnetic grab to latch on)
Magnetic box (use magnetic grab to pick up)
Vines
Spikes (damage players and push them back)
Crushers (fall on players and hurt them a lot)
Saw (likes spikes but moves)