## Final Production Schedule
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms still | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Completed | 2023-09-11
GDD | Rework The GDD | Joseph | High | Completed | 2023-09-13
Level | Area 1 minimap | Joseph | High | Completed | 2023-09-15
Level | Area 2 minimap | Joseph | High | Completed | 2023-09-19
Level | Area 3 minimap | Joseph | High | Completed | 2023-09-19
Level | Area 4 minimap | Joseph | High | Completed | 2023-09-19
Level | World Map | Joseph | High | Completed | 2023-09-14
Level | Platform moving | Joseph | med | Not Started | 2023-09-23
Level | Area 1 skeleton | Joseph | High | Completed | 2023-09-19
Level | Area 2 skeleton | Joseph | High | In Progress | 2023-09-19
Level | Area 3 skeleton | Joseph | High | In Progress | 2023-09-26
Level | Area 4 skeleton | Joseph | High | In Progress | 2023-09-26
Level | One-way Platforms | Joseph | Med | Completed | 2023-09-11
Level | Area 1 | Joseph | High | Completed | 2023-10-01
Level | Area 2 | Joseph | High | Completed | 2023-10-01
Level | Area 3 | Joseph | High | In Progress | 2023-10-01
Level | Area 4 | Joseph | High | In Progress | 2023-10-01
Game Art
| Animations (Player) | Wyatt(Artist)
Game Art | Running Animation | Wyatt(Artist) | High | Finished | 2023-09-30
Game Art | Jumping Animation | Wyatt(Artist) | High | Finished | 2023-10-13
Game Art | Shooting Animation | Wyatt(Artist) | High | Finished | 2023-10-13
Game Art | Slicing Animation | Wyatt(Artist) | High | Finished | 2023-10-13
Game Art | Walking Animation | Wyatt(Artist) | High | Finished | 2023-09-30
Game Art | Idle Animation | Wyatt(Artist) | High | Finished | 2023-09-30
Game Art | Animations (Enemy) | Wyatt(Artist)
Game Art | Walker Walk | Wyatt(Artist) | High | Finished | 2023-10-04
Game Art | Walker Slice | Wyatt(Artist) | High | Finished | 2023-10-04
Game Art | Scout Fly | Wyatt(Artist) | High | Finished | 2023-10-25
Game Art | Sprites (Enemy) | Wyatt(Artist)
Game Art | Walker | Wyatt(Artist) | High | Finished | 2023-09-25
Game Art | Hunter | Wyatt(Artist) | High | Finished | 2023-09-25
Game Art | Scout | Wyatt(Artist) | Medium | Finished | 2023-10-18
Game Art | Sprites (Player) | Wyatt(Artist)
Game Art | Beta-14 (multi color) | Wyatt(Artist) | Low | Finished | 2023-09-15
Game Art
Game Art | Background Art | Wyatt(Artist)
Game Art | Area 1 Outside | Wyatt(Artist) | High | Finished | 2023-10-18
Game Art | Area 1 Inside | Wyatt(Artist) | High | Finished | 2023-10-18
Game Art | Area 2 Outside | Wyatt(Artist) | High | Finished | 2023-10-18
Game Art | Area 2 Inside | Wyatt(Artist) | High | Finished | 2023-10-18
Game Art | Area 3 Outside | Wyatt(Artist) | Medium | In Progress | 2023-12-04
Game Art | Area 3 Inside | Wyatt(Artist) | Medium | Not Started | 2023-12-04
Game Art | Area 4 Outside | Wyatt(Artist) | Medium | Not Started | 2023-12-04
Game Art | Area 4 Inside | Wyatt(Artist) | Medium | Not Started | 2023-12-04
Game Art | Cutscene Art | Wyatt(Artist)
Game Art | Escape | Wyatt(Artist) | Low | Not Started | 2023-12-04
Game Art
Game Art | Platform Art | Wyatt(Artist)
Game Art | Platform Rotted | Wyatt(Artist) | Low | Finished | 2023-09-30
Game Art | Platform New | Wyatt(Artist) | Low | Finished | 2023-09-30
Game Art | Game Documents | Wyatt(Artist)
Game Art | Updated GDD | Wyatt(Artist) | High | Finished | 2023-11-29
Game Art | Updated 1 pager | Wyatt(Artist) | High | Finished | 2023-11-29
Game Art | Updated 10 pager | Wyatt(Artist) | High | Finished | 2023-11-29
Game Art | Feedback Results | Wyatt(Artist) | High | Finished | 2023-11-14
UI & Menu
Player UI/ Looks | Health Bar | Emanuel | High | Finished
Player UI/ Looks | Enegry Bar | Emanuel | High | Finished
Pause/Main Menu | Menu icons | Emanuel | Med | Finished
Pause/Main Menu | Menu Border | Emanuel | Med | Finished
Pause/Main Menu | Menu Buttons Fix | Emanuel | High | Finished
Pause/Main Menu | Create a Control Panel | Emanuel | Med | Finished
Game Assets
Health pack | Find & import a placeholder | Emanuel | Low | Finished
Traps | Find & import a placeholder | Emanuel | Low | Finished
Key Card | Find & import a placeholder | Emanuel | Low | Finished
Asset Packs
Forest Pack | Find & Import pack | Emanuel | Low | Finished
Sci-fi Pack | Find & Import pack | Emanuel | Low | Finished
Background
Parallax Effect | Test it | Emanuel | Low | Finished
Implementation | Import into area 1 & 2 | Emanuel | Low | Finished
Implementation | Import into area 3 & 4 | Emanuel | Low | N/a
Beta Test Feedback
Mini-map | Update Improve Minimap | Emanuel | Med | Finished
Mini-map | Player Location indicator | Emanuel | Med | Finished
Mini-map | Indicator for Key Items/ Objects | Emanuel | Med | In progress
Player UI | key/item management | Emanuel | Low | N/a
Death Screen | Setup death/ respawn screen | Emanuel | Low | Finished
Death Screen | Animate It (optinal) | Emanuel | Low | N/a
UI | Disable/ Fix Area 5 Map Key | Emanuel | Med | Finished
Menu | Sprint not Listed in Controls | Emanuel | Low | In progress
Coding | Door with a lock and a key (check for fix) | Raphael Brown | High | Completed | 2023-04-17
Coding | Lava – on the floor and on walls (are like spikes) | Raphael Brown | High | Not Started
Coding | Magnetic hooks (use magnetic grab to latch on) | Raphael Brown | High
Coding | Magnetic box (use magnetic grab to pick up) | Raphael Brown | High
Coding | Vines | Raphael Brown | High
Coding | Spikes (damage players and push them back) | Raphael Brown | High
Coding | Crushers (fall on players and hurt them a lot) | Raphael Brown | High
Coding | Saw (likes spikes but moves) | Raphael Brown | Med
Coding | Crates (breakable tiles but respawn when player leave room) | Raphael Brown | Med
2023-03-10
coding | Dash | Raphael Brown | High | Completed | 2023-09-19
coding | Water Pump shoot | Raphael Brown | High | Not Started | 2023-09-19
coding | Water pump jump | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab box | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab shoot | Raphael Brown | High | Not Started | 2023-09-26
coding | Claw wall climb. | Raphael Brown | High | Not Started
2023-03-10
coding | Walk | Raphael Brown | High | Completed | 2023-03-10
coding | Jump | Raphael Brown | High | Completed
coding | Fix sticking to walls (ground check need to be changed.) | Raphael Brown | High | Not Started | 2023-09-19
coding | Water pump button | Raphael Brown | High | Not Started | 2023-09-26
coding | Magnetic grab button | Raphael Brown | High | Not Started | 2023-09-19
coding | Energy resource (use for combat) | Raphael Brown | High | Not Started | 2023-09-19
coding | Water resource (used for pump) | Raphael Brown | High | Not Started
coding | Saving System | Raphael Brown
coding | Save rooms that track progress and what the player has | Raphael Brown
coding | Check point system(For falling into pits and lava) | Raphael Brown
Enemy AI | Walk | Raphael Brown | High | Completed
Enemy AI | Shoot player. | Raphael Brown | High | Completed
Enemy AI | Attack player – melee | Raphael Brown | High | Completed
Enemy AI | Spawner (when player leaves room) | Raphael Brown | High | Completed
Enemy AI | HP | Raphael Brown | High | Completed
Sound
Playable Character |  |  |  |  | N/A
Footsteps |  | Marcus Queiro |  | N/A | Sept 8th
Weapon Sounds(Gun, Blade) |  | Marcus Queiro |  | Done | Sept 8th
Death |  | Marcus Queiro |  | Done | Sept 26th
Abilities(Dash, Energy Blaster, Grapplehook) |  | Marcus Queiro |  | Done | Sept 8th
Hurt |  | Marcus Queiro |  | Done | Sept 8th
Pick up items |  | Marcus Queiro |  | Done
Enemies |  |  |  |  | Sept 12th
Hunter pounce |  | Marcus Queiro |  | Done | Sept 12th
Hunter hurt |  | Marcus Queiro |  | Done | Sept 12th
Hunter death |  | Marcus Queiro |  | Done | Sept 18th
Walker rifle |  | Marcus Queiro |  | Done | Sept 18th
Walker death |  | Marcus Queiro |  | Done | Sept 18th
Walker hurt |  | Marcus Queiro |  | Done
Environment |  |  |  |  | Sept 24th
Player Interaction |  | Marcus Queiro |  | Done | Sept 24th
Level 1 Music |  | Marcus Queiro |  | Done | Sept 24th
Level 2 Music |  | Marcus Queiro |  | Done | Sept 24th
Level 3 Music |  | Marcus Queiro |  | Done | Sept 24th
Level 4 Music |  | Marcus Queiro |  | Done
UI |  |  |  |  | Sep 8th
Button Sound |  | Marcus Queiro |  | Done
Marcus Queiro
Beta Results |  | Marcus Queiro |  |  | Nov 15th
Respawn noise |  | Marcus Queiro |  | Done | Nov 15th
Fix switch noise(too loud) |  | Marcus Queiro |  | Done | Nov 15th
Adjustment of footsetps being too loud |  | Marcus Queiro |  | Done