## Marcus Queiro(Sound Effects)
Assets | Status
Sound
Playable Character
Footsteps | N/A
Weapon Sounds(Gun, Blade) | Draft Done
Death | Draft Done
Abilities(Dash, Double Jump, Magnetic Grab, Claw Grip, Water Pump)
Hurt | Draft Done
Pick up items | Draft Done
Enemies
Hunter pounce | Draft Done
Hunter hurt | Draft Done
Hunter death | Draft Done
Walker rifle | Draft Done
Walker death | Draft Done
Walker hurt | Draft Done
Environment
Level Background
Player Interaction | Draft Done
UI
Button Sound | Draft Done

## Joseph Pak (Poducer and Design)
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms still | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Completed | 2023-09-11
GDD | Rework The GDD | Joseph | High | Completed | 2023-09-13
Level | Area 1 minimap | Joseph | High | In Progress | 2023-09-15
Level | Area 2 minimap | Joseph | High | Not Started | 2023-09-19
Level | Area 3 minimap | Joseph | High | Not Started | 2023-09-19
Level | Area 4 minimap | Joseph | High | Not Started | 2023-09-19
Level | Area 5 minimap | Joseph | High | Not Started | 2023-09-19
Level | World Map | Joseph | High | Completed | 2023-09-14
Level | Platform moving | Joseph | med | Not Started | 2023-09-23
Level | Area 1 | Joseph | High | Not Started | 2023-09-19
Level | Area 2 | Joseph | High | Not Started | 2023-09-19
Level | Area 3 | Joseph | High | Not Started | 2023-09-26
Level | Area 4 | Joseph | High | Not Started | 2023-09-26
Level | Area 5 | Joseph | High | Not Started | 2023-09-26
Level | One-way Platforms | Joseph | Med | Completed | 2023-09-11
coding | Dash | Joseph | High | Completed | 2023-03-10
coding | Water Pump shoot | Joseph | High | Not Started | 2023-09-19
coding | Water pump jump | Joseph | High | Not Started | 2023-09-19
coding | Magnetic grab box | Joseph | High | Not Started | 2023-09-26
coding | Magnetic grab shoot | Joseph | High | Not Started | 2023-09-26
coding | Claw wall climb. | Joseph | High | Not Started | 2023-09-26
coding | Walk | Joseph | High | Completed | 2023-03-10
coding | Jump | Joseph | High | Completed | 2023-03-10
coding | Water pump button | Joseph | High | Not Started | 2023-09-19
coding | Magnetic grab button | Joseph | High | Not Started | 2023-09-26
coding | Energy resource (use for combat) | Joseph | High | Not Started | 2023-09-19
coding | Water resource (used for pump) | Joseph | High | Not Started | 2023-09-19

## Wyatt(Artist)
Assets | Task | Who | Priority | Status | Due Date
Game Art
| Running Animation |  | Medium | Not Started | 2023-09-30
| Platform Art |  | High | Not Started | 2023-09-23
| Tutorial Drawings |  | Low | Not Started | 2023-10-02
| Enemy Art |  | High | Not Started | 2023-09-25
| Outermost Background |  | Medium | Not Started | 2023-10-02
Coding
| Menu Escape |  | High | Not Started | 2023-09-12
| Volume |  | High | Not Started | 2023-09-12
| Fullscreen toggle |  | Medium | Not Started | 2023-10-02

## Emanuel(designer)
Assets | Task | Who | Priority | Status | Due Date
UI & Menu
Player UI | Health Bar | Emanuel | High | N/a | N/a
Player UI | Enegry Bar | Emanuel | High | N/a | N/a
Pause/Main Menu | Menu icons | Emanuel | Med | N/a | N/a
Pause/Main Menu | Menu Border | Emanuel | Med | N/a | N/a
Pause/Main Menu | Redesign Background | Emanuel | Med | N/a | N/a
VFX
Particle Effect | Fire | Emanuel | Low | N/a | N/a
Shader/ Particle Effect | Lava Pool/ Shader | Emanuel | Low | N/a | N/a
Level
Room | Design a Save Room | Emanuel | High | N/a | N/a
Room | Design a Resource Room | Emanuel | High | N/a | N/a

## Raphael Brown(Programmer)
Assets | Task | Who | Priority | Status | Due Date
Coding | Door with a lock and a key (check for fix) | Raphael Brown | High | Completed | 2023-04-17
Coding | Lava – on the floor and on walls (are like spikes) | Raphael Brown | High | Not Started
Coding | Magnetic hooks (use magnetic grab to latch on) | Raphael Brown | High
Coding | Magnetic box (use magnetic grab to pick up) | Raphael Brown | High
Coding | Vines | Raphael Brown | High
Coding | Spikes (damage players and push them back) | Raphael Brown | High
Coding | Crushers (fall on players and hurt them a lot) | Raphael Brown | High
Coding | Saw (likes spikes but moves) | Raphael Brown | Med
Energy resource (use for combat)
Water resource (used for pump)
Saving System
Save rooms that track progress and what the player has
Check point system(For falling into pits and lava)
Enemy AI | Walk | Raphael Brown
Enemy AI | Shoot player. | Raphael Brown
Enemy AI | Attack player – melee | Raphael Brown
Enemy AI | Spawner (when player leaves room) | Raphael Brown
Enemy AI | HP | Raphael Brown