## Sheet1
Assets | task | who | priority | status | due
Player | animation | Jason | High | Not Started | 2023-04-21
Player | concept and design | Jason | High | Completed | 2023-02-24
Player | UI meter and health | Emanuel | Med | Not Started | 2023-04-20
Player | Profile | Jason | Low | Not Started | 2023-02-26
Player | sounds | Simi | Med | Not Started | 2023-02-27
Player animaton | Walking | Jason | High | Not Started | 2023-02-28
Player animaton | Jumping | Jason | Med | Not Started | 2023-03-01
Player animaton | Idle | Jason | High | Not Started | 2023-03-02
Player animaton | Shooting | Jason | Med | Not Started | 2023-03-03
Player animaton | Dash | Jason | Low | Not Started | 2023-03-04
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | In Progress | 2023-03-06
Level | Background art | Joseph | Med | Not Started | 2023-03-25
Level | Platform layout | Joseph | Med | Not Started | 2023-03-10
Level | Level tile art | Joseph | Med | Not Started | 2023-03-11
Deserted Robot | concept and design | Jason | Low | Not Started | 2023-03-08
Enemy Walker | Concept and design | Jason | High | Completed | 2023-03-09
Enemy Walker | Animation | Jason | High | Not Started | 2023-04-05
Enemy Hunter | Concept and design | Jason | Low | Not Started | 2023-03-10
Enemy Hunter | Animation | Jason | Low | Not Started | 2023-04-08
Boss | concept/ design | Jason | High | In Progress | 2023-03-25
Boss | Animation | Jason | High | Not Started | 2023-04-12
Boss | Fight Pattern | Jason | High | Not Started | 2023-03-26
Traps/ hazards | concept/ design | Emanuel | Low | In Progress | 2023-04-15
coding | Platfroms | Joseph | High | Not Started | 2023-03-13
coding | Character Controls | Laila | High | Completed | 2023-03-04
coding | Enemy AI | Laila | High | Not Started | 2023-04-15
coding | Combat | Laila | High | In Progress | 2023-04-01
coding | Level and EXP | Laila | High | Not Started | 2023-04-15
coding | Saving | Laila | High | Not Started | 2023-03-25
UI | HP and Resource | Emanuel | Med | Not Started | 2023-04-15
UI | Current weapons | Emanuel | Med | Not Started | 2023-04-15
Menu | Start menu | Emanuel | Med | Not Started | 2023-04-20
Menu | Pause menu | Emanuel | Med | Not Started | 2023-04-20
Menu | Settings | Emanuel | Med | Not Started | 2023-04-20
Menu | Inventory |  | Med | Not Started | 2023-04-02
Menu | Skill tree |  | Med | Not Started | 2023-04-04
Audio Music | Menu screen theme | Simi | Low | Not Started
Audio Music | BGM for each level/area | Simi | High | Not Started | 2023-04-03
Audio Music | Combat themes | Simi | Low | Not Started
Audio Music | Boss themes | Simi | Low | Not Started
Audio Music | Credits theme | Simi | Low | Not Started
Audio SFX | Player footsteps | Simi | High | Not Started | 2023-04-01
Audio SFX | Player weapons sounds | Simi | High | Completed | 2023-02-28
Audio SFX | UI interaction | Simi | Med | Completed | 2023-02-28
Audio SFX | Robot sounds for enemy | Simi | High | Not Started | 2023-04-01
Audio SFX | Robot sounds for player | Simi | High | Not Started | 2023-04-07
Audio SFX | Boss-specific sounds | Simi | Low | Not Started | 2023-04-28
Audio SFX | Death sounds Player | Simi | High | Not Started | 2023-04-07
Audio SFX | Death sounds Enemy | Simi | Med | Not Started | 2023-04-14
Audio SFX | Certain objects in an area | Simi | Low | Not Started | 2023-04-28
Item | HP | Emanuel | Low | Not Started | 2023-04-05
Item | Energy | Emanuel | Low | Not Started | 2023-04-07
Item | Gear Exp | Emanuel | Low | Not Started | 2023-04-08