## Marcus Queiro(Sound Effects)
Assets | Status
Sound
Playable Character
Footsteps | N/A
Weapon Sounds(Gun, Blade) | Draft Done
Death | Draft Done
Abilities(Dash, Double Jump, Magnetic Hook, Electric Run, Invisible Dash)
Hurt | Draft Done
Pick up items | Draft Done
Enemies
Hunter pounce
Hunter hurt
Hunter death
Walker rifle
Walker melee
Walker death
Walker hurt
Environment
Level Background
Player Interaction
UI
Button Sound | Draft Done

## Joseph Pak (Poducer and Design)
Assets | Task | Who | Priority | Status | Due Date
coding | respawn | Joseph | High | Completed | 2023-04-17
coding | Platfroms | Joseph | High | Not Started | 2023-03-13
Level | Simple world Layout | Joseph | Med | Completed | 2023-03-05
Level | First Area Layout | Joseph | High | Completed | 2023-03-06
coding | checkpoint | Joseph | High | In Progress | 2023-04-17
Level | Background art | Joseph | Med | In Progress | 2023-03-25
Level | Platform layout | Joseph | Med | In Progress | 2023-03-10
Level | Level tile art | Joseph | Med | Completed | 2023-03-11
Level | Rework first level layout | Joseph | High | Not Started | 2023-09-11
GDD | Rework The GDD | Joseph | High | In Progress | 2023-09-09

## Wyatt(Artist)
Assets | Task | Who | Priority | Status | Due Date
Game Art
| Running Animation |  | Medium | Not Started | 2023-09-30
| Platform Art |  | High | Not Started | 2023-09-23
| Tutorial Drawings |  | Low | Not Started | 2023-10-02
| Enemy Art |  | High | Not Started | 2023-09-25
| Outermost Background |  | Medium | Not Started | 2023-10-02
Coding
| Menu Escape |  | High | Not Started | 2023-09-12
| Volume |  | High | Not Started | 2023-09-12
| Fullscreen toggle |  | Medium | Not Started | 2023-10-02

## Emanuel(designer)
Assets | Task | Who | Priority | Status | Due Date
UI & Menu
Player UI | Health Bar | Emanuel | High | N/a | N/a
Player UI | Enegry Bar | Emanuel | High | N/a | N/a
Pause/Main Menu | Menu icons | Emanuel | Med | N/a | N/a
Pause/Main Menu | Menu Border | Emanuel | Med | N/a | N/a
Pause/Main Menu | Redesign Background | Emanuel | Med | N/a | N/a

## Raphael Brown(Programmer)
Assets | Task | Who | Priority | Status | Due Date